## StandUpMeetings
2019-03-11 |  | 2019-03-12 |  | 2019-03-13 |  | 2019-03-14 |  | 2019-03-15
Completed task | PBI-2 : Completed Market dabase design | Completed task | Pragnya on sick leave | Completed task | Pragnya on sick leave | Completed task | Pragnya on sick leave | Completed task
Planned task | PBI-3 : Development in progress | Planned task | Pragnya on sick leave | Planned task | Pragnya on sick leave | Planned task | Pragnya on sick leave | Planned task
Blockers | No blockers | Blockers |  | Blockers |  | Blockers |  | Blockers
2019-03-11 |  | 2019-03-12 |  | 2019-03-13 |  | 2019-03-14 |  | 2019-03-15
Completed task | PBI-2 : Completed Market dabase design | Completed task |  | Completed task |  | Completed task |  | Completed task
Planned task | PBI-3 : Development in progress | Planned task |  | Planned task |  | Planned task |  | Planned task
Blockers | No blockers | Blockers |  | Blockers |  | Blockers |  | Blockers
2019-03-11 |  | 2019-03-12 |  | 2019-03-13 |  | 2019-03-14 |  | 2019-03-15
Completed task | PBI-2 : Completed Market dabase design | Completed task |  | Completed task |  | Completed task |  | Completed task
Planned task | PBI-3 : Development in progress | Planned task |  | Planned task |  | Planned task |  | Planned task
Blockers | No blockers | Blockers |  | Blockers |  | Blockers |  | Blockers
2019-03-11 |  | 2019-03-12 |  | 2019-03-13 |  | 2019-03-14 |  | 2019-03-15
Completed task | PBI-2 : Completed Market dabase design | Completed task |  | Completed task |  | Completed task |  | Completed task
Planned task | PBI-3 : Development in progress | Planned task |  | Planned task |  | Planned task |  | Planned task
Blockers | No blockers | Blockers |  | Blockers |  | Blockers |  | Blockers
2019-03-11 |  | 2019-03-12 |  | 2019-03-13 |  | 2019-03-14 |  | 2019-03-15
Completed task | PBI-2 : Completed Market dabase design | Completed task |  | Completed task |  | Completed task |  | Completed task
Planned task | PBI-3 : Development in progress | Planned task |  | Planned task |  | Planned task |  | Planned task
Blockers | No blockers | Blockers |  | Blockers |  | Blockers |  | Blockers
2019-03-11 |  | 2019-03-12 |  | 2019-03-13 |  | 2019-03-14 |  | 2019-03-15
Completed task | PBI-2 : Completed Market dabase design | Completed task |  | Completed task |  | Completed task |  | Completed task
Planned task | PBI-3 : Development in progress | Planned task |  | Planned task |  | Planned task |  | Planned task
Blockers | No blockers | Blockers |  | Blockers |  | Blockers |  | Blockers

## ProductBacklogItem(PBI)
PBI_ID | ProductBacklogItemName | ProductBacklogItemDescription
1 | The Food Market Requirements | As Product Owner, I want to define Food market product requirements
2 | Design MarketDB | As a Architect, I want to design Market database
3 | Create MarketDB | As a Architect, I want to create Market database.
4 | Rest API - e-marketApi | As a Architect, I want to develop a middle ware e-marketApi
5 | e-market web application | As Product Owner, I want to define the e-market web application required
6 | Perfreview e-market | As Architect, I want to review the performance of e-market application 1. Database tuning 2. Optimize e-marketApi 3. Review e-market application
7 | Host e-market online | As Product Owner, I want to host this application on internet.

## Iteration1
PBI_ID | Story Card | Story Name | Story Description
1 | 1 | Shop Requirements | As a Developer, I want to gather a shop details requirements
| 2 | Contact Requirements | As a Developer, I want to gather a shop contacts details requirements
| 3 | Product Requirements | As a Developer, I want to gather a product details requirements
| 4 | Order Requirements | As a Developer, I want to gather a product details requirements
| 5 | Payment Requirement | As a Developer, I want to gather a payment details requirements
| 6 | Billing Requirement | As a Developer, I want to gather a billing details requirements
| 7 | Customer Requirement | As a Developer, I want to gather a customer details requirements
2 | 1 | Design Shop table | As a developer, I want to design a shop table.
| 2 | Design Contact table | As a developer, I want to design a contact table.
| 3 | Design Product table | As a developer, I want to design a Product table.
| 4 | Design Order table | As a developer, I want to design a Order table.
| 5 | Design Payment table | As a developer, I want to design a Payment table.
| 6 | Design OrderStatus table | As a developer, I want to design a OrderStatus table.
| 7 | Design QuantityType table | As a developer, I want to design a QuantityType table.
| 8 | Design Billing table | As a developer, I want to design a Billing table.
| 9 | Design Customer table | As a developer, I want to design a Customer table.
| 10 | Design ShopProductMapping table | As a developer, I want to design a ShopProductMapping table.
3 | 1 | Create Table | As a developer, I want to create shop table in marketting database
| 2 | Create Contact | As a developer, I want to create contact table in marketting database
| 3 | Create Product | As a developer, I want to create Product table in marketting database
| 4 | Create Orders | As a developer, I want to create Orders table in marketting database
| 5 | Create Payment | As a developer, I want to create Payment table in marketting database
| 6 | Create Customer | As a developer, I want to create Customer table in marketting database
| 7 | Create Billing | As a developer, I want to create Billing table in marketting database
| 8 | Create ShopProductMapping | As a developer, I want to create shopProductMapping table in marketting database
| 9 | Create QuantityType | As a developer, I want to create QuantityType table in marketting database
| 10 | Create OrderStatus | As a developer, I want to create OrderStatus table in marketting database
| 11 | Create Shop stored Procedures | SP1 => Name: GetAllShop Input: Shop_Name Output: should return => Shop_No, ShopName, Contact_Number1, Contact_Number2
SP2 => Name: GetAllShopProducts Input: Shop_Name Output: should return => Shop_No, ShopName, Product_Name, Product_Type, Product_Price
SP3 => Name: GetAllShopProducts Input: Shop_Name Output: should return => Shop_No, ShopName, Product_Name, Product_Type, Product_Price
SP4 => Name: InsertShop Input: Shop_Name, Shop_Owner, Shop_Address, Contact_Number1, Contact_Number2(optional parameter) Output: VOID Test: Verify that records inserted into shop table
SP5 => Name: UpdateShop Input: Shop_Name, Shop_Address, Contact_Number1, Contact_Number2(optional parameter) Output: VOID Test: Verify that records
| 12 | Contact table stored procedures
| 13 | Product table stored procedures
| 14 | Order table stored procedures
| 15 | Payment table stored procedures
| 16 | Billing table stored procedures
| 17 | Customer table stored procedures